## Sheet1
Task ID | Sprint Week | Task Description | Owner | Status | Priority | Start Date | Due Date | Progress (%) | Comments
WK0-01 | 0 | Finalize Project Charter (v0.1) | Hamza | Done | High | 2025-07-22 | 2025-07-23 | 100
WK0-02 | 0 | Create GitHub repository & branch protection | Hamza | Not Started | High | 2025-07-22 | 2025-07-24 | 0
WK0-03 | 0 | Add initial README, LICENSE, .gitignore | Hamza | Not Started | Medium | 2025-07-23 | 2025-07-25 | 0
WK0-04 | 0 | Set up CI workflow (GitHub Actions) | Hamza | Not Started | Medium | 2025-07-24 | 2025-07-27 | 0
WK1-01 | 1 | Prototype NSE/BSE filings crawler | Intern | Not Started | High | 2025-07-27 | 2025-08-03 | 0
WK1-02 | 1 | Prototype Mutual Fund factsheet scraper | Intern | Not Started | High | 2025-07-27 | 2025-08-03 | 0
WK1-03 | 1 | Define Postgres schema for filings & financials | Hamza | Not Started | High | 2025-07-29 | 2025-08-03 | 0
WK1-04 | 1 | Write ETL job (Python, Pandas) with unit tests | Hamza | Not Started | High | 2025-07-29 | 2025-08-03 | 0
WK2-01 | 2 | Implement AAOIFI ratio calculator microservice | Hamza | Not Started | High | 2025-08-03 | 2025-08-10 | 0
WK2-02 | 2 | Create automated tests (>90% coverage) | Intern | Not Started | Medium | 2025-08-03 | 2025-08-10 | 0
WK3-01 | 3 | Set up vLLM server with Llama‑3‑8B | Hamza | Not Started | High | 2025-08-10 | 2025-08-17 | 0
WK3-02 | 3 | Develop RAG pipeline for Explain‑Why panel | Hamza | Not Started | High | 2025-08-10 | 2025-08-17 | 0
WK3-03 | 3 | Expose REST endpoint + swagger docs | Hamza | Not Started | Medium | 2025-08-12 | 2025-08-17 | 0
WK4-01 | 4 | Build Search UI & result page (Next.js) | Frontend Dev | Not Started | High | 2025-08-17 | 2025-08-24 | 0
WK4-02 | 4 | Implement Daily Movers dashboard | Frontend Dev | Not Started | Medium | 2025-08-17 | 2025-08-24 | 0
WK4-03 | 4 | Integrate Watch‑list CRUD with backend | Frontend Dev | Not Started | High | 2025-08-19 | 2025-08-24 | 0
WK5-01 | 5 | Develop alert engine (Celery + SES) | Hamza | Not Started | High | 2025-08-24 | 2025-08-31 | 0
WK5-02 | 5 | Mobile responsiveness & accessibility | Frontend Dev | Not Started | Medium | 2025-08-24 | 2025-08-31 | 0
WK5-03 | 5 | Instrumentation (Prometheus, Grafana, Sentry) | Hamza | Not Started | Medium | 2025-08-26 | 2025-08-31 | 0
WK6-01 | 6 | Deploy beta to staging (EKS) | Hamza | Not Started | High | 2025-08-31 | 2025-09-04 | 0
WK6-02 | 6 | Onboard 10 pilot users & gather feedback | Hamza | Not Started | High | 2025-08-31 | 2025-09-07 | 0
WK6-03 | 6 | Bug fixes & backlog grooming for v0.2 | Hamza | Not Started | Medium | 2025-09-02 | 2025-09-09 | 0